## Risk Register
Risk ID | Risk Title | Risk Description | Category | Strategic Goal / Compliance Objective | Risk Drivers | Potential Impacts | Risk Owner | Date Identified | Likelihood (Inherent) | Impact (Inherent) | Inherent Rating | Existing Controls | Control Effectiveness | Appetite Alignment | Priority Decision | Treatment Objective | Residual Likelihood | Residual Impact | Residual Rating | Status of Risk Action Plan | Review Frequency | Next Review Date
R-2025-03 | Facility failure due to deferred maintenance | Deferred maintenance could result in facility failure affecting student safety and operations | Facilities & Infrastructure | Student safety and well-being | Aging facilities; limited capital funding; reactive maintenance practices | Disruption to learning environments; emergency closures; increased long-term repair costs; parent concern about planning | Facilities Manager | 2025-11-28 | 4 – Likely | 4 – Major | High (13-16) | Annual inspections; work-order tracking; safety compliance checks | Adequate | Exceeds appetite | Priority for Action Plan | Reduce likelihood of major facility failure | 3 – Possible | 3 – Medium | Moderate (5-12) | In Progress | Quarterly | 2026-07-28
R-2025-07 | Cybersecurity breach | Unauthorized access to district systems could compromise sensitive data and disrupt operations | Technology & Data | Community trust | Legacy systems; insufficient MFA coverage; staff phishing vulnerability | Loss of confidential data; service interruptions; reputational harm; privacy compliance breaches | IT Manager | 2025-12-04 | 3 – Possible | 5 – Catastrophic | High (13-16) | Firewalls; basic staff awareness training; backups | Developing | Exceeds appetite | Priority for Action Plan | Reduce likelihood of unauthorized access and impact of downtime | 2 – Unlikely | 4 – Major | Moderate (5-12) | Not Started | Semi-annual | 2026-06-15
R-2025-11 | Recruitment and retention challenges | Difficulty attracting and retaining qualified staff may impact service delivery and student supports | People & Culture | Student safety and well-being | Competitive labour market; rural/remote location; pay compression; housing availability | Program delivery gaps; increased workload; declining morale; higher turnover costs | HR Manager | 2025-12-10 | 1 – Rare | 3 – Medium | Moderate (5-12) | Posting processes; onboarding; mentorship program | Developing | Approaching appetite | Monitor or Targeted Action Plan | Reduce likelihood of vacancies and impact on continuity of services | 3 – Possible | 3 – Medium | Moderate (5-12) | Monitor Only | Other | 2026-06-30

## Dashboard
Risk ID | Risk Title | Category | Strategic Goal / Compliance Objective | Inherent Rating | Residual Rating | Appetite Alignment | Status
R-2025-03 | Facility failure due to deferred maintenance | Facilities & Infrastructure | Student safety and well-being | High (13-16) | Moderate (5-12) | Exceeds appetite | In Progress
R-2025-07 | Cybersecurity breach | Technology & Data | Community trust | High (13-16) | Moderate (5-12) | Exceeds appetite | Not Started
R-2025-11 | Recruitment and retention challenges | People & Culture | Student safety and well-being | Moderate (5-12) | Moderate (5-12) | Approaching appetite | Monitor Only

## Lookups
RiskCategories | StrategicGoals | LikelihoodScale | ImpactScale | ControlEffectivenessList | PriorityDecisionList | StatusList | AppetiteAlignmentList | ReviewFrequencyList | RatingScale
People & Culture | Student safety and well-being | 1 – Rare | 1 – Low | Weak | Not a Priority | Not Started | Within appetite | Quarterly | Very Low (1-2)
Financial Sustainability | Financial stewardship | 2 – Unlikely | 2 – Minor | Developing | Monitor Only | Paused or deferred | Approaching appetite | Semi-annual | Low (3-4)
Governance & Compliance | Educational innovation | 3 – Possible | 3 – Medium | Adequate | Priority for Action Plan | In progress | Exceeds appetite | Annual | Moderate (5-12)
Educational Program Delivery | Community trust | 4 – Likely | 4 – Major | Strong | Monitor or Targeted Action Plan | Complete | Unclear or NA | Other | High (13-16)
Facilities & Infrastructure |  | 5 – Almost Certain | 5 – Catastrophic |  |  | Cancelled |  |  | Extreme (17-25)
Technology & Data | [5 empty] | Monitor only
Reputation & Community Trust | [5 empty] | Accept the risk
Political & social climate
Physical climate & environment